## Charts
| Design Option | Duration | Complexity
| Simulators | 7.1333 | 15
| Infra+Clients Front End | 7.8333 | 12
| TopDev1+TopDev2 | 8.5333 | 12
| TopDev2 | 9.4667 | 12
| Normal | 9.9333 | 12
| Sub-Critical | 13.4333 | 5
Bonus: | One Dev Only | 26 | 1
Normal
Sub-Critical
One Developer

## Normal
ID | Activity | Depends on | Reduced Dependencies | Number of Dependencies Per Acticity
1 | Requirements |  |  |  | P |  | 1
2 | Architecture | 1 | 1 | 1 | N | Number of Activities | 23
3 | Project Design | 2 | 2 | 1 | E | Total Dependencies | 33
4 | Test Plan | 22 | 22 | 1
5 | Test Harness | 4 | 4 | 1 | C | Complexity | 12
6 | Logging | 22 | 22 | 1
7 | Security | 6 | 6 | 1
8 | Pub/Sub | 6 | 6 | 1
9 | Resource A | 22 | 22 | 1
10 | Resource B | 22 | 22 | 1
11 | Resource Access A | 9,23 | 9,23 | 2
12 | Resource Access B | 10,23 | 10,23 | 2
13 | Resource Access C | 23 | 23 | 1
14 | EngineA | 12,13 | 12,13 | 2
15 | EngineB | 12,13 | 12,13 | 2
16 | EngineC | 23 | 23 | 1
17 | ManagerA | 14,15,11 | 14,15,11 | 3
18 | ManagerB | 15,16 | 15,16 | 2
19 | Client App1 | 17,18 | 17,18 | 2
20 | Client App2 | 17 | 17 | 1
21 | System Testing | 5,19,20 | 5,19,20 | 3
22 | M0 | 3 | 3 | 1
23 | M1 | 7,8 | 7,8 | 2

## Subcritical
ID | Activity | Depends on | Reduced Dependencies | Number of Dependencies Per Acticity
1 | Requirements |  |  |  | P |  | 1
2 | Architecture | 1 | 1 | 1 | N | Number of Activities | 23
3 | Project Design | 2 | 2 | 1 | E | Total Dependencies | 26
4 | Test Plan | 20 | 20 | 1
5 | Test Harness | 4 | 4 | 1 | C | Complexity | 5
6 | Logging | 22 | 22 | 1
7 | Security | 6 | 6 | 1
8 | Pub/Sub | 6 | 6 | 1
9 | Resource A | 10 | 10 | 1
10 | Resource B | 8 | 8 | 1
11 | Resource Access A | 9 | 9 | 1
12 | Resource Access B | 13 | 13 | 1
13 | Resource Access C | 23 | 23 | 1
14 | EngineA | 12,11 | 12,11 | 2
15 | EngineB | 12 | 12 | 1
16 | EngineC | 15 | 15 | 1
17 | ManagerA | 14 | 14 | 1
18 | ManagerB | 16 | 16 | 1
19 | Client App1 | 17,18 | 17,18 | 2
20 | Client App2 | 17 | 17 | 1
21 | System Testing | 5,19 | 5,19 | 2
22 | M0 | 3 | 3 | 1
23 | M1 | 7,8 | 7,8 | 2

## TopDev2
ID | Activity | Depends on | Reduced Dependencies | Number of Dependencies Per Acticity
1 | Requirements |  |  |  | P |  | 1
2 | Architecture | 1 | 1 | 1 | N | Number of Activities | 23
3 | Project Design | 2 | 2 | 1 | E | Total Dependencies | 33
4 | Test Plan | 22 | 22 | 1
5 | Test Harness | 4 | 4 | 1 | C | Complexity | 12
6 | Logging | 22 | 22 | 1
7 | Security | 6 | 6 | 1
8 | Pub/Sub | 6 | 6 | 1
9 | Resource A | 22 | 22 | 1
10 | Resource B | 22 | 22 | 1
11 | Resource Access A | 9,23 | 9,23 | 2
12 | Resource Access B | 10,23 | 10,23 | 2
13 | Resource Access C | 23 | 23 | 1
14 | EngineA | 12,13 | 12,13 | 2
15 | EngineB | 12,13 | 12,13 | 2
16 | EngineC | 23 | 23 | 1
17 | ManagerA | 14,15,11 | 14,15,11 | 3
18 | ManagerB | 15,16 | 15,16 | 2
19 | Client App1 | 17,18 | 17,18 | 2
20 | Client App2 | 17 | 17 | 1
21 | System Testing | 5,19,20 | 5,19,20 | 3
22 | M0 | 3 | 3 | 1
23 | M1 | 7,8 | 7,8 | 2

## TopDev1+TopDev2
ID | Activity | Depends on | Reduced Dependencies | Number of Dependencies Per Acticity
1 | Requirements |  |  |  | P |  | 1
2 | Architecture | 1 | 1 | 1 | N | Number of Activities | 23
3 | Project Design | 2 | 2 | 1 | E | Total Dependencies | 33
4 | Test Plan | 22 | 22 | 1
5 | Test Harness | 4 | 4 | 1 | C | Complexity | 12
6 | Logging | 22 | 22 | 1
7 | Security | 6 | 6 | 1
8 | Pub/Sub | 6 | 6 | 1
9 | Resource A | 22 | 22 | 1
10 | Resource B | 22 | 22 | 1
11 | Resource Access A | 9,23 | 9,23 | 2
12 | Resource Access B | 10,23 | 10,23 | 2
13 | Resource Access C | 23 | 23 | 1
14 | EngineA | 12,13 | 12,13 | 2
15 | EngineB | 12,13 | 12,13 | 2
16 | EngineC | 23 | 23 | 1
17 | ManagerA | 14,15,11 | 14,15,11 | 3
18 | ManagerB | 15,16 | 15,16 | 2
19 | Client App1 | 17,18 | 17,18 | 2
20 | Client App2 | 17 | 17 | 1
21 | System Testing | 5,19,20 | 5,19,20 | 3
22 | M0 | 3 | 3 | 1
23 | M1 | 7,8 | 7,8 | 2

## Infra + Clients Front End
ID | Activity | Depends on | Reduced Dependencies | Number of Dependencies Per Acticity
1 | Requirements |  |  |  | P |  | 1
2 | Architecture | 1 | 1 | 1 | N | Number of Activities | 25
3 | Project Design | 2 | 2 | 1 | E | Total Dependencies | 35
4 | Test Plan | 22 | 22 | 1
5 | Test Harness | 4 | 4 | 1 | C | Complexity | 12
6 | Logging |  |  | 1
7 | Security | 6 | 6 | 1
8 | Pub/Sub | 6 | 6 | 1
9 | Resource A | 22 | 22 | 1
10 | Resource B | 22 | 22 | 1
11 | Resource Access A | 9,23 | 9 | 1
12 | Resource Access B | 10,23 | 10 | 1
13 | Resource Access C | 22,23 | 22 | 1
14 | EngineA | 12,13 | 12,13 | 2
15 | EngineB | 12,13 | 12,13 | 2
16 | EngineC | 22,23 | 22 | 1
17 | ManagerA | 14,15,11 | 14,15,11 | 3
18 | ManagerB | 15,16 | 15,16 | 2
19 | Client App1 | 17,18 | 17,18 | 2
20 | Client App2 | 17 | 17 | 1
21 | System Testing | 5,19,20 | 5,19,20 | 3
22 | M0 | 3,24,25 | 3,24,25 | 3
23 | M1 | 7,8 | 7,8 | 2
24 | Client App1 Design | 23 | 23 | 1
25 | Client App2 Design | 23 | 23 | 1

## Simulators
ID | Activity | Depends on | Reduced Dependencies | Number of Dependencies Per Acticity
1 | Requirements |  |  |  | P |  | 1
2 | Architecture | 1 | 1 | 1 | N | Number of Activities | 29
3 | Project Design | 2 | 2 | 1 | E | Total Dependencies | 42
4 | Test Plan | 22 | 22 | 1
5 | Test Harness | 4 | 4 | 1 | C | Complexity | 15
6 | Logging |  |  | 1
7 | Security | 6 | 6 | 1
8 | Pub/Sub | 6 | 6 | 1
9 | Resource A | 22 | 22 | 1
10 | Resource B | 22 | 22 | 1
11 | Resource Access A | 9,23 | 9 | 1
12 | Resource Access B | 10,23 | 10 | 1
13 | Resource Access C | 22,23 | 22 | 1
14 | EngineA | 12,13 | 12,13 | 2
15 | EngineB | 12,13 | 12,13 | 2
16 | EngineC | 22,23 | 22 | 1
17 | ManagerA | 14,15,11 | 14,15,11 | 3
18 | ManagerB | 15,16 | 15,16 | 2
19 | Client App1 Integration | 17,18,28 | 17,18,28 | 3
20 | Client App2 Integration | 17,29 | 17,29 | 2
21 | System Testing | 5,19,20 | 5,19,20 | 3
22 | M0 | 3,24,25 | 3,24,25 | 3
23 | M1 | 7,8 | 7,8 | 2
24 | Client App1 Design | 23 | 23 | 1
25 | Client App2 Design | 23 | 23 | 1
26 | ManagerA Simulator | 22 | 22 | 1
27 | ManagerB Simulator | 22 | 22 | 1
28 | Client App1 | 26,27,24 | 26,27 | 2
29 | Client App2 | 26,25 | 26 | 1